## Project Dashboard
Project Dashboard
Project Name: | Globtec |  |  | Highlights
Report Date | 2018-03-11 |  |  | 1. Found dataProviderID related changes in all component and completed.
Sub-Project | Sprint 5 |  |  | 2. Team is working on critical issues like a. typeahead valuelist related b. Panel and auto height related issues.
Status |  |  |  | 3. Given functional demo of relation, article and sales order module.
Current Work On Hand
Form Getting Converted
[5 empty] | Name |  |  | %Completed / Status
|  |  |  | 1 | Contracts form conversions |  |  | 100%
|  |  |  | 2 | Warehoulse -> Warehouse Location, Move, |  |  | 100%
|  |  |  | 3 | Warehoulse -> To delivery, put rules |  |  | 100%
|  |  |  | 4 | Warehoulse -> Stock, Inventory, tracking |  |  | 100%
Onsite Team KPIs
KPI & Team |  | Rakesh Sharma | Bhavesh Panchal |  |  | Nilav Patel | Promod Sahu
Estimated Vs Actual time per user stories
Defect ration per user stories
Defect Removal Efficiency
Communication
Working on items
Jay | Working on grid issues
Binkal | Tree list control and form conversions
Bhavesh | Feneko product configurator
Nilav | Feneko Portal
Rakesh | Critical issues
Pramod | Working on ware house forms conversions
Open Items
1 | Few links are shared with Robrecht regarding servoy issues and so needs to discuss with servoy team for it.
2 | Globis to get back on the KPI benchmark : Robrecht and Karel to discussion and propose.
3 | For "Fevicon" we need database fields and so pending. Field related details get it done by Robrecht.
. Communication data is not available
Note on B28: Shaival Trivedi: User stories estimation > 23 hours KPI in RED if estimation > 10% of estimated time. KPI in GREEN if estimation <= 10% of estimated time User stories estimation < 23 hours KPI in RED if estimation > 5% of estimated time. KPI in GREEN if estimation <= 5% of estimated time
Note on B30: Shaival Trivedi: User stories with estimation > 40 hours KPI in RED if number of defects > 15 KPI in ORANGE if number of defects BETWEEN 7 AND 14 KPI in GREEN if estimation <= 7 User stories with estimation > 23 hours KPI in RED if number of defects > 10 KPI in ORANGE if number of defects BETWEEN 5 AND 9 KPI in GREEN if estimation <= 5 User stories with estimation > 15 and < 23 hours KPI in RED if number of defects > 7 KPI in ORANGE if number of defects BETWEEN 4 AND 7 KPI in GREEN if estimation <= 4 User stories with estimation < 10 KPI in RED if number of defects > 3 KPI in GREEN if estimation < =3
Note on B32: Shaival Trivedi: Critical Bugs/ Total Bugs (critical + non-critical) per day ----------------------------------- The defect fixing on the code developed by other developers. This will test the defect identification skill as well. During initial period, we will keep this as a Performance Indicator rather than Key Performance indicator. We will measure the data for coming week and then define the bench mark to measure the indicator
Note on B34: Shaival Trivedi: To be measured every 15 days . Point 1 to 5 (1 = poor , 5 = excellence) 1. Measurement will be done during demo. 2. Measurement will be done while communication with Globis team members.

## Weekly Data
|  | Nilav | KPI 1 | Bhavesh | KPI 1 | Rakesh | KPI 1 | Pramod | KPI 1
| >23 KPI's | 2 | 0 | 2 | 0 | 1 | 1 | 3 | 0
| <23 KPI's | 7 | 2 | 22 | 2 | 18 | 4 | 12 | 0
|  | Completed | Pending | Total
| Enhancements | 31 | 6 | 37
| Isssues | 24 | 11 | 35
Sum of Actual Duration |  |  | Week | [10 empty] | Calculation Purpose Only
Person Name | Activity Description | Estimation | Week 7 | Week 8 | Week 9 | Week 10 | Grand Total |  |  | Type | Status | Employee Name | KPI Type | Estimated Hrs. | Spent Hours | Diff | KPI 1 | KPI 2 | KPI 3
Bhavesh | 5718 - NG General issues - pin task bar when scrolling down | 4 | 0 | 4 | 0 | 0 | 4 |  |  | Enhancement | Done | Bhavesh | KPI 1 | 4 | 4 | 0 | 0
| 5824 - Prevent a user to close the ng client or to click back / forward button | 14 | 0 | 8 | 4.5 | 0 | 12.5 |  |  | Enhancement | InProgress | Bhavesh | KPI 1 | 14 | 12.5 | 1.5 | 0
| 5827 - NG - Product Configurator | 45 | 7 | 23 | 0 | 0 | 30 |  |  | Enhancement | OnHold | Bhavesh | KPI 1 | 45 | 30 | 15 | 0
| NG - Removing hover effect on dropdown when disabled | 1 | 1 | 0 | 0 | 0 | 1 |  |  | Enhancement | Done | Bhavesh | KPI 1 | 1 | 1 | 0 | 0
| NG - Servoy Console Valuelist Error | 30 | 30.5 | 0 | 0 | 0 | 30.5 |  |  | Issue | OnHold | Bhavesh | KPI 1 | 30 | 30.5 | -0.5 | 0
| R & D of cumub io dashboard | 1 | 1 | 0 | 0 | 0 | 1 |  |  | Enhancement | OnHold | Bhavesh | KPI 1 | 1 | 1 | 0 | 0
| 5835 - NG General - typeahead doesn't show all values | 8 | 0 | 0 | 13.5 | 3.5 | 17 |  |  | Issue | InProgress | Bhavesh | KPI 1 | 8 | 17 | -9 | 1
| 5839 - NG General - Change style for Servoy Tabpanel | 2 | 0 | 0 | 1.5 | 0 | 1.5 |  |  | Enhancement | Done | Bhavesh | KPI 1 | 2 | 1.5 | 0.5 | 0
| 5829 - NG General issues - selection of record jumps automatically to another record | 10 | 0 | 0 | 4.5 | 0 | 4.5 |  |  | Issue | Done | Bhavesh | KPI 1 | 10 | 4.5 | 5.5 | 0
| 5875 - Dropdown valuelist related issue | 4 | 0 | 0 | 3.5 | 0 | 3.5 |  |  | Issue | Done | Bhavesh | KPI 1 | 4 | 3.5 | 0.5 | 0
| 5853 - NG - Translation tab's form is not showing | 2 | 0 | 0 | 2 | 0 | 2 |  |  | Issue | Done | Bhavesh | KPI 1 | 2 | 2 | 0 | 0
| 5856 - NG - Needs to restrict second popup at the time of logout | 2 | 0 | 0 | 2 | 0 | 2 |  |  | Enhancement | Done | Bhavesh | KPI 1 | 2 | 2 | 0 | 0
| 5862 - NG - Panel Related Issues | 3 | 0 | 0 | 3 | 0 | 3 |  |  | Issue | Done | Bhavesh | KPI 1 | 3 | 3 | 0 | 0
| 5771 - NG General issues - specific formatters | 8 | 0 | 0 | 4 | 0 | 4 |  |  | Issue | InProgress | Bhavesh | KPI 1 | 8 | 4 | 4 | 0
| NG General - Provide handler for clicking a notification tile | 1 | 0 | 0 | 0 | 1 | 1 |  |  | Issue | Done | Bhavesh | KPI 1 | 1 | 1 | 0 | 0
| 5880 - NG General - Provide handler for clicking a notification tile | 1.5 | 0 | 0 | 1.5 | 0 | 1.5 |  |  | Enhancement | Done | Bhavesh | KPI 1 | 1.5 | 1.5 | 0 | 0
| 5867 - NG General - Extra API to set filters in grid | 1 | 0 | 0 | 0 | 1 | 1 |  |  | Issue | OnHold | Bhavesh | KPI 1 | 1 | 1 | 0 | 0
| 5884 - NG - Contracts - Mandatory Field is not showing | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | Issue | Done | Bhavesh | KPI 1 | 1.5 | 1.5 | 0 | 0
| Preventing Browser to go back, refresh and tab close, restrict when isDeveloper | 14 | 0 | 0 | 0 | 2 | 2 |  |  | Issue | Done | Bhavesh | KPI 1 | 14 | 2 | 12 | 0
| 5924 - NG - dataProviderID correction in components | 2.5 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | Issue | Done | Bhavesh | KPI 1 | 2.5 | 2.5 | 0 | 0
| NG General issues - bar main functionalities does not move when minimizing the top bar | 5 | 0 | 0 | 0 | 10 | 10 |  |  | Issue | Done | Bhavesh | KPI 1 | 5 | 10 | -5 | 1
| NG - Screen title bar disappears on home (dashboard) screen | 1 | 0 | 0 | 0 | 1 | 1 |  |  | Issue | Done | Bhavesh | KPI 1 | 1 | 1 | 0 | 0
| NG - Valuelist type ahead | 5 | 0 | 0 | 0 | 5 | 5 |  |  | Issue | Done | Bhavesh | KPI 1 | 5 | 5 | 0 | 0
| 5907 - Textbox with valuelist issue | 14 | 0 | 0 | 0 | 12.5 | 12.5 |  |  | Issue | InProgress | Bhavesh | KPI 2 | 14 | 12.5 | 1.5 | 0
Bhavesh Total |  |  | 39.5 | 35 | 40 | 40 | 154.5
Nilav | 5730 - NG General - adjust favicon and html (browser) title | 8 | 10 | 0 | 0 | 0 | 10 |  |  | Enhancement | OnHold | Nilav | KPI 1 | 8 | 10 | -2 | 1
| 5746 - NG Screen Zone | 8 | 0 | 8 | 0 | 0 | 8 |  |  | Issue | OnHold | Nilav | KPI 1 | 8 | 8 | 0 | 0
| CancelRequired field validation for all the controls | 8 | 10 | 0 | 0 | 0 | 10 |  |  | Enhancement | Done | Nilav | KPI 1 | 8 | 10 | -2 | 1
| 5834 - Dynamic Height | 54 | 18 | 32 | 8 | 0 | 58 |  |  | Enhancement | Done | Nilav | KPI 1 | 54 | 58 | -4 | 0
| 5829 - NG General issues - selection of record jumps automatically to another record | 10 | 0 | 0 | 8 | 0 | 8 |  |  | Issue | Done | Nilav | KPI 1 | 10 | 8 | 2 | 0
| 5857 - Feneko Portal | 128 | 0 | 0 | 23.5 | 38 | 61.5 |  |  | Enhancement | InProgress | Nilav | KPI 1 | 128 | 61.5 | 66.5 | 0
| CSS related | 2 | 0 | 0 | 1.5 | 0 | 1.5 |  |  | Issue | Done | Nilav | KPI 1 | 2 | 1.5 | 0.5 | 0
| 5888 - NG - Panel height Related Issue in Article Form and Others | 16 | 0 | 0 | 0 | 4 | 4 |  |  | Issue | InProgress | Nilav | KPI 1 | 16 | 4 | 12 | 0
| 5924 - NG - dataProviderID correction in components | 2.5 | 0 | 0 | 0 | 2 | 2 |  |  | Issue | Done | Nilav | KPI 1 | 2.5 | 2 | 0.5 | 0
Nilav Total |  |  | 38 | 40 | 41 | 44 | 163
Pramod | 5832 - NG - General Company Parameter Form conversions | 72 | 16 | 40 | 1.5 | 0 | 57.5 |  |  | Enhancement | Done | Pramod | KPI 1 | 72 | 57.5 | 14.5 | 0
| Article Forms Conversion | 12 | 8 | 0 | 0 | 0 | 8 |  |  | Enhancement | Done | Pramod | KPI 1 | 12 | 8 | 4 | 0
| Billing and Relations Forms Conversion | 12 | 8 | 0 | 0 | 0 | 8 |  |  | Enhancement | Done | Pramod | KPI 1 | 12 | 8 | 4 | 0
| Financial plan Forms Conversion | 13 | 8 | 0 | 0 | 0 | 8 |  |  | Enhancement | Done | Pramod | KPI 1 | 13 | 8 | 5 | 0
| 5844 - NG - Contracts - Form Conversion | 32 | 0 | 0 | 19.5 | 3.5 | 23 |  |  | Enhancement | InProgress | Pramod | KPI 1 | 32 | 23 | 9 | 0
| 5850 - NG - Company - Concern Parameter Forms conversation | 14 | 0 | 0 | 10.5 | 0 | 10.5 |  |  | Enhancement | Done | Pramod | KPI 1 | 14 | 10.5 | 3.5 | 0
| 5852 - NG - Webshop user form conversion | 4 | 0 | 0 | 3 | 0 | 3 |  |  | Enhancement | Done | Pramod | KPI 1 | 4 | 3 | 1 | 0
| Financial Plan Redesign and Purchase Order Redesign | 2 | 0 | 0 | 1 | 0 | 1 |  |  | Enhancement | Done | Pramod | KPI 1 | 2 | 1 | 1 | 0
| Functional Flow Related | 18 | 0 | 0 | 6 | 6 | 12 |  |  | Enhancement | Done | Pramod | KPI 1 | 18 | 12 | 6 | 0
| 5924 - NG - dataProviderID correction in components | 2.5 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | Issue | Done | Pramod | KPI 1 | 2.5 | 2.5 | 0 | 0
| 5918 - NG - Warehouse - Warehouse Location, Warehouse Move, Put Rules, To Delivery, etc... | 26 | 0 | 0 | 0 | 15 | 15 |  |  | Enhancement | Done | Pramod | KPI 1 | 26 | 15 | 11 | 0
| 5919 - NG - Complaint forms conversion | 7 | 0 | 0 | 0 | 4 | 4 |  |  | Enhancement | Done | Pramod | KPI 1 | 7 | 4 | 3 | 0
| Sales order form Redesign | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | Enhancement | Done | Pramod | KPI 1 | 0.5 | 0.5 | 0 | 0
| 5943 - NG - Warehouse - Form conversion for the to pack without tracking, warehouse stock, inventory, etc... | 17 | 0 | 0 | 0 | 6.5 | 6.5 |  |  | Enhancement | Done | Pramod | KPI 1 | 17 | 6.5 | 10.5 | 0
| 5937 - NG - No limitation on data length in a field? | 12 | 0 | 0 | 0 | 5 | 5 |  |  | Enhancement | Done | Pramod | KPI 1 | 12 | 5 | 7 | 0
Pramod Total |  |  | 40 | 40 | 41.5 | 43 | 164.5
Rakesh | 5709- NG Screen Main Groups and sub groups | 6 | 8 | 0 | 0 | 0 | 8 |  |  | Enhancement | Done | Rakesh | KPI 1 | 6 | 8 | -2 | 1
| 5711 - NG General : enhancements for custom views on list forms redirect on single records come by filter | 6 | 0 | 9 | 0 | 0 | 9 |  |  | Enhancement | Done | Rakesh | KPI 1 | 6 | 9 | -3 | 1
| 5775 - NG General issues - Upload document | 10 | 0 | 2.5 | 8 | 0 | 10.5 |  |  | Issue | Done | Rakesh | KPI 1 | 10 | 10.5 | -0.5 | 0
| 5784 - NG General - application freeze on clicking home button | 5 | 0 | 5 | 0 | 0 | 5 |  |  | Issue | Done | Rakesh | KPI 1 | 5 | 5 | 0 | 0
| Case Type -> Unable to edit in grid (Jasper given) | 8 | 10.5 | 0 | 0 | 0 | 10.5 |  |  | Issue | OnHold | Rakesh | KPI 1 | 8 | 10.5 | -2.5 | 1
| Change in CSS for disable and check it's functionality | 2 | 0 | 2 | 0 | 0 | 2 |  |  | Enhancement | Done | Rakesh | KPI 1 | 2 | 2 | 0 | 0
| Fixing data dataproviderID related error getting at runtime of globtecdevexcomponents control | 3 | 0 | 3 | 0 | 0 | 3 |  |  | Issue | Done | Rakesh | KPI 1 | 3 | 3 | 0 | 0
| List Selection (MultiSelect) control checkbox related changes | 4 | 0 | 4 | 0 | 0 | 4 |  |  | Enhancement | Done | Rakesh | KPI 1 | 4 | 4 | 0 | 0
| Multi-select in list selection for grouping in console page. | 6 | 0 | 9.5 | 0 | 0 | 9.5 |  |  | Enhancement | Done | Rakesh | KPI 1 | 6 | 9.5 | -3.5 | 1
| NG Form Conversion : Financial Plan module into responsive layout | 12 | 8 | 0 | 0 | 0 | 8 |  |  | Enhancement | Done | Rakesh | KPI 1 | 12 | 8 | 4 | 0
| NG General - getProgramName issue on click Dashboard from Breadcrumb panel | 3 | 0 | 3 | 0 | 0 | 3 |  |  | Issue | Done | Rakesh | KPI 1 | 3 | 3 | 0 | 0
| onDataChange (…) event parameter not getting value at backend for textbox, dropdown and checkbox control and fixed it. | 2.5 | 2.5 | 0 | 0 | 0 | 2.5 |  |  | Issue | Done | Rakesh | KPI 1 | 2.5 | 2.5 | 0 | 0
| 5830 - NG General issues - suggestions attachment functionality | 28 | 0 | 0 | 34.5 | 6 | 40.5 |  |  | Enhancement | Done | Rakesh | KPI 1 | 28 | 40.5 | -12.5 | 1
| Functional Flow Related | 18 | 0 | 6 | 0 | 0 | 6 |  |  | Enhancement | Done | Rakesh | KPI 1 | 18 | 6 | 12 | 0
| 5877 - NG - Datagrid UI related | 2.5 | 0 | 0 | 0 | 2 | 2 |  |  | Enhancement | Done | Rakesh | KPI 1 | 2.5 | 2 | 0.5 | 0
| Control visibility issue in sales order (warehouse) | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 |  |  | Issue | Done | Rakesh | KPI 1 | 1.5 | 1.5 | 0 | 0
| 5888 - NG - Panel height Related Issue in Article Form and Others | 20 | 0 | 0 | 0 | 24.5 | 24.5 |  |  | Issue | InProgress | Rakesh | KPI 3 | 20 | 24.5 | -4.5 | 0
| 5924 - NG - dataProviderID correction in components | 2.5 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | Issue | Done | Rakesh | KPI 1 | 2.5 | 0.5 | 2 | 0
| 5947 - NG General - Bug in expanding tabs when showing same form in different tabs | 8 | 0 | 0 | 0 | 2 | 2 |  |  | Issue | InProgress | Rakesh | KPI 1 | 8 | 2 | 6 | 0
Rakesh Total |  |  | 29 | 44 | 42.5 | 36.5 | 152
Jay | 5905 - Datagrid multiple record selection | 10 | 0 | 0 | 0 | 7.5 | 7.5 |  |  | Enhancement | Done | Jay | KPI 1 | 10 | 7.5 | 2.5 | 0
| 5746 - Issue in selection for same grid | 5 | 0 | 0 | 0 | 0.5 | 0.5 |  |  | Issue | InProgress | Jay | KPI 1 | 5 | 0.5 | 4.5 | 0
| 5900 - Article Type Issue | 3 | 0 | 0 | 0 | 3.5 | 3.5 |  |  | Issue | Done | Jay | KPI 1 | 3 | 3.5 | -0.5 | 1
| 5873 NG General - refresh data behaviour | 30 | 0 | 0 | 0 | 25.5 | 25.5 |  |  | Issue | Done | Jay | KPI 1 | 30 | 25.5 | 4.5 | 0
| Meeting | 2.5 | 0 | 0 | 0 | 2.5 | 2.5 |  |  | Enhancement | Done | Jay | KPI 1 | 2.5 | 2.5 | 0 | 0
Jay Total |  |  | 0 | 0 | 0 | 39.5 | 39.5
Grand Total |  |  | 146.5 | 159 | 165 | 203 | 673.5

## RAW Data
Week | Axosoft Number | Activity Description | Person Name | Estimation | Actual Duration | Comments | Type | Status | Date | #Of Issues | Issue #
Week 7 |  | NG - Servoy Console Valuelist Error | Bhavesh | 30 | 6.5 | Server MarkUp Id getting same and so cause an issue. As discussed with robrecht put on-hold. | Issue | OnHold
Week 7 |  | NG - Servoy Console Valuelist Error | Bhavesh | 30 | 1 |  | Issue | OnHold
Week 7 |  | NG - Servoy Console Valuelist Error | Bhavesh | 30 | 7 |  | Issue | OnHold
Week 7 |  | NG - Removing hover effect on dropdown when disabled | Bhavesh | 1 | 1 |  | Enhancement | Done
Week 7 |  | NG - Servoy Console Valuelist Error | Bhavesh | 30 | 8 |  | Issue | OnHold
Week 7 |  | NG - Servoy Console Valuelist Error | Bhavesh | 30 | 8 |  | Issue | OnHold
Week 7 |  | R & D of cumub io dashboard | Bhavesh | 1 | 1 |  | Enhancement | OnHold
Week 7 | 5827 | 5827 - NG - Product Configurator | Bhavesh | 45 | 2 | Phase I | Enhancement | OnHold
Week 7 | 5827 | 5827 - NG - Product Configurator | Bhavesh | 45 | 5 | Phase I | Enhancement | OnHold
Week 8 | 5827 | 5827 - NG - Product Configurator | Bhavesh | 45 | 5 | Phase I | Enhancement | OnHold
Week 8 | 5718 | 5718 - NG General issues - pin task bar when scrolling down | Bhavesh | 4 | 3 |  | Enhancement | Done
Week 8 | 5718 | 5718 - NG General issues - pin task bar when scrolling down | Bhavesh | 4 | 1 |  | Enhancement | Done
Week 8 | 5827 | 5827 - NG - Product Configurator | Bhavesh | 45 | 2 | Phase I | Enhancement | OnHold
Week 8 | 5827 | 5827 - NG - Product Configurator | Bhavesh | 45 | 8 | Phase I | Enhancement | OnHold
Week 8 | 5827 | 5827 - NG - Product Configurator | Bhavesh | 45 | 8 | Phase I | Enhancement | OnHold
Week 8 | 5824 | 5824 - Prevent a user to close the ng client or to click back / forward button | Bhavesh | 14 | 8 | One issue came from yannik | Enhancement | InProgress |  | KPI 1
Week 7 |  | Article Forms Conversion | Pramod | 12 | 8 |  | Enhancement | Done
Week 7 |  | Financial plan Forms Conversion | Pramod | 13 | 8 |  | Enhancement | Done
Week 7 |  | Billing and Relations Forms Conversion | Pramod | 12 | 8 |  | Enhancement | Done
Week 7 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 7 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 8 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 8 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 8 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 8 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 8 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 8 |  | Enhancement | Done
Week 7 |  | CancelRequired field validation for all the controls | Nilav | 8 | 8 |  | Enhancement | Done
Week 7 |  | CancelRequired field validation for all the controls | Nilav | 8 | 2 |  | Enhancement | Done
Week 7 | 5730 | 5730 - NG General - adjust favicon and html (browser) title | Nilav | 8 | 6 | Database field is pending and needs to be discuss with Robrecht | Enhancement | OnHold
Week 7 | 5730 | 5730 - NG General - adjust favicon and html (browser) title | Nilav | 8 | 4 | Database field is pending and needs to be discuss with Robrecht | Enhancement | OnHold
Week 7 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 2 |  | Enhancement | Done
Week 7 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 8 |  | Enhancement | Done
Week 7 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 8 |  | Enhancement | Done
Week 8 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 4 |  | Enhancement | Done
Week 8 | 5746 | 5746 - NG Screen Zone | Nilav | 8 | 4 | Server MarkUp Id getting same and so cause an issue. As discussed with robrecht put on-hold. | Issue | OnHold
Week 8 | 5746 | 5746 - NG Screen Zone | Nilav | 8 | 4 | Server MarkUp Id getting same and so cause an issue. As discussed with robrecht put on-hold. | Issue | OnHold
Week 8 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 4 |  | Enhancement | Done
Week 8 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 8 |  | Enhancement | Done
Week 8 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 8 |  | Enhancement | Done
Week 8 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 8 |  | Enhancement | Done
Week 7 |  | NG Form Conversion : Financial Plan module into responsive layout | Rakesh | 12 | 6 |  | Enhancement | Done
Week 7 |  | NG Form Conversion : Financial Plan module into responsive layout | Rakesh | 12 | 2 |  | Enhancement | Done
Week 7 |  | Case Type -> Unable to edit in grid (Jasper given) | Rakesh | 8 | 6 | Needs to check with Robrecht | Issue | OnHold
Week 7 |  | onDataChange (…) event parameter not getting value at backend for textbox, dropdown and checkbox control and fixed it. | Rakesh | 2.5 | 2.5 |  | Issue | Done
Week 7 |  | Case Type -> Unable to edit in grid (Jasper given) | Rakesh | 8 | 4.5 |  | Issue | OnHold
Week 7 | 5709 | 5709- NG Screen Main Groups and sub groups | Rakesh | 6 | 8 |  | Enhancement | Done
Week 8 |  | List Selection (MultiSelect) control checkbox related changes | Rakesh | 4 | 4 |  | Enhancement | Done
Week 8 |  | Fixing data dataproviderID related error getting at runtime of globtecdevexcomponents control | Rakesh | 3 | 3 |  | Issue | Done
Week 8 |  | Multi-select in list selection for grouping in console page. | Rakesh | 6 | 4.5 |  | Enhancement | Done
Week 8 |  | Multi-select in list selection for grouping in console page. | Rakesh | 6 | 5 |  | Enhancement | Done
Week 8 | 5784 | 5784 - NG General - application freeze on clicking home button | Rakesh | 5 | 5 |  | Issue | Done
Week 8 |  | NG General - getProgramName issue on click Dashboard from Breadcrumb panel | Rakesh | 3 | 3 |  | Issue | Done
Week 8 | 5711 | 5711 - NG General : enhancements for custom views on list forms redirect on single records come by filter | Rakesh | 6 | 6 |  | Enhancement | Done
Week 8 | 5711 | 5711 - NG General : enhancements for custom views on list forms redirect on single records come by filter | Rakesh | 6 | 3 |  | Enhancement | Done
Week 8 | 5775 | 5775 - NG General issues - Upload document | Rakesh | 10 | 2.5 | GOLObject and others | Issue | Done
Week 8 |  | Change in CSS for disable and check it's functionality | Rakesh | 2 | 2 |  | Enhancement | Done
Week 8 |  | Functional Flow Related | Rakesh | 18 | 6 |  | Enhancement | Done
Week 9 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 |  | Excise and WebService | Enhancement | Done | 2018-02-26
Week 9 | 5824 | 5824 - Prevent a user to close the ng client or to click back / forward button | Bhavesh | 14 | 3 |  | Enhancement | Done | 2018-02-26
Week 9 | 5835 | 5835 - NG General - typeahead doesn't show all values | Bhavesh | 8 | 3.5 | Not possible due to 500 records rendering only. | Issue | InProgress | 2018-02-26 | KPI 1 | 5907
Week 9 | 5839 | 5839 - NG General - Change style for Servoy Tabpanel | Bhavesh | 2 | 1.5 |  | Enhancement | Done | 2018-02-26
Week 9 | 5775 | 5775 - NG General issues - Upload document | Rakesh | 10 | 4 | GOLObject and others | Enhancement | Done | 2018-02-26
Week 9 | 5829 | 5829 - NG General issues - selection of record jumps automatically to another record | Nilav | 10 | 6 |  | Issue | Done | 2018-02-26
Week 9 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 2.5 |  | Enhancement | Done | 2018-02-26
Week 9 | 5775 | 5775 - NG General issues - Upload document | Rakesh | 10 | 4 | GOLObject and others | Issue | Done | 2018-02-26
Week 9 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 2 |  | Enhancement | Done | 2018-02-26
Week 9 |  | Functional Flow Related | Pramod | 18 | 3 |  | Enhancement | Done | 2018-02-26
Week 9 | 5832 | 5832 - NG - General Company Parameter Form conversions | Pramod | 72 | 1.5 |  | Enhancement | Done | 2018-02-26
Week 9 | 5844 | 5844 - NG - Contracts - Form Conversion | Pramod | 32 | 3.5 | Contracts -> Contract | Enhancement | InProgress | 2018-02-26
Week 9 | 5844 | 5844 - NG - Contracts - Form Conversion | Pramod | 32 | 4 | Billing Group, To Invoice, Stock Summary and Location Stock | Enhancement | InProgress | 2018-02-27
Week 9 | 5850 | 5850 - NG - Company - Concern Parameter Forms conversation | Pramod | 14 | 5 |  | Enhancement | Done | 2018-02-27
Week 9 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 8 |  | Enhancement | Done | 2018-02-27
Week 9 | 5835 | 5835 - NG General - typeahead doesn't show all values | Bhavesh | 8 | 3 | Not possible due to 500 records rendering only. | Issue | InProgress | 2018-02-27 | KPI 1 | 5907
Week 9 | 5829 | 5829 - NG General issues - selection of record jumps automatically to another record | Bhavesh | 10 | 4.5 | Issue 1. | Issue | Done | 2018-02-27 | KPI 3
Week 9 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 3 | 1. Added role in webshop user 2. Functional understanding | Enhancement | InProgress | 2018-02-27
Week 9 | 5834 | 5834 - Dynamic Height | Nilav | 54 | 6 | Made changes into it as suggested by robrecht 2. Panel height issue also fixed. 3. Worked on first tab which is selected when we are navigating that is fixed now. | Enhancement | Done | 2018-02-27
Week 9 | 5875 | 5875 - Dropdown valuelist related issue | Bhavesh | 4 | 1 |  | Issue | Done | 2018-02-28
Week 9 | 5824 | 5824 - Prevent a user to close the ng client or to click back / forward button | Bhavesh | 14 | 1.5 | One issue came from yannik | Enhancement | Done | 2018-02-28 | KPI 1
Week 9 | 5853 | 5853 - NG - Translation tab's form is not showing | Bhavesh | 2 | 2 |  | Issue | Done | 2018-02-28
Week 9 | 5856 | 5856 - NG - Needs to restrict second popup at the time of logout | Bhavesh | 2 | 2 |  | Enhancement | Done | 2018-02-28
Week 9 | 5862 | 5862 - NG - Panel Related Issues | Bhavesh | 3 | 2 | Concern parameter form is not loading properly as expected due to only detail form. | Issue | Done | 2018-02-28
Week 9 | 5829 | 5829 - NG General issues - selection of record jumps automatically to another record | Nilav | 10 | 2 | Issue 2. | Issue | Done | 2018-02-28
Week 9 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 6 |  | Enhancement | InProgress | 2018-02-28
Week 9 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 6.5 |  | Enhancement | InProgress | 2018-03-01
Week 9 |  | CSS related | Nilav | 2 | 1.5 |  | Issue | Done | 2018-03-01
Week 9 | 5850 | 5850 - NG - Company - Concern Parameter Forms conversation | Pramod | 14 | 5.5 |  | Enhancement | Done | 2018-02-28
Week 9 | 5852 | 5852 - NG - Webshop user form conversion | Pramod | 4 | 3 |  | Enhancement | Done | 2018-02-28
Week 9 | 5844 | 5844 - NG - Contracts - Form Conversion | Pramod | 32 | 7 | Contracts -> Articles, Project and other few forms. | Enhancement | InProgress | 2018-03-01
Week 9 | 5875 | 5875 - Dropdown valuelist related issue | Bhavesh | 4 | 2.5 | Solved dropdown binding issue in purchase order form. | Issue | Done | 2018-03-01
Week 9 | 5835 | 5835 - NG General - typeahead doesn't show all values | Bhavesh | 8 | 3.5 |  | Issue | InProgress | 2018-03-01 | KPI 1 | 5907
Week 9 | 5862 | 5862 - NG - Panel Related Issues | Bhavesh | 3 | 1 | Removed scrollbar from the viewer forms. | Issue | Done | 2018-03-01
Week 9 | 5771 | 5771 - NG General issues - specific formatters | Bhavesh | 8 | 1 |  | Issue | InProgress | 2018-03-01
Week 9 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 8 |  | Enhancement | InProgress | 2018-03-02
Week 9 | 5835 | 5835 - NG General - typeahead doesn't show all values | Bhavesh | 8 | 3.5 |  | Issue | InProgress | 2018-03-02 | KPI 1 | 5907
Week 9 | 5880 | 5880 - NG General - Provide handler for clicking a notification tile | Bhavesh | 1.5 | 1.5 |  | Enhancement | Done | 2018-03-02
Week 9 | 5771 | 5771 - NG General issues - specific formatters | Bhavesh | 8 | 3 |  | Enhancement | InProgress | 2018-03-02
Week 9 |  | Financial Plan Redesign and Purchase Order Redesign | Pramod | 2 | 1 |  | Enhancement | Done | 2018-03-01
Week 9 | 5844 | 5844 - NG - Contracts - Form Conversion | Pramod | 32 | 5 | Contracts -> Billing form conversasion related. | Enhancement | InProgress | 2018-03-02
Week 9 |  | Functional Flow Related | Pramod | 18 | 3 |  | Enhancement | Done | 2018-03-02
Week 9 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 8 |  | Enhancement | Done | 2018-02-28
Week 9 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 8 |  | Enhancement | Done | 2018-03-01
Week 9 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 8 |  | Enhancement | Done | 2018-03-02
Week 10 | 5905 | 5905 - Datagrid multiple record selection | Jay | 10 | 7.5 |  | Enhancement | Done | 2018-03-05
Week 10 | 5745 | 5746 - Issue in selection for same grid | Jay | 5 | 0.5 |  | Issue | InProgress | 2018-03-05
Week 10 | 5835 | 5835 - NG General - typeahead doesn't show all values | Bhavesh | 8 | 2.5 | added typeahead in textbox & change field in price routing type form | Enhancement | Done | 2018-03-05 | KPI 1 | 5907
Week 10 | 5867 | 5867 - NG General - Extra API to set filters in grid | Bhavesh | 1 | 1 |  | Issue | OnHold | 2018-03-05
Week 10 | 5884 | 5884 - NG - Contracts - Mandatory Field is not showing | Bhavesh | 1.5 | 1.5 |  | Issue | Done | 2018-03-05
Week 10 | 5824 | Preventing Browser to go back, refresh and tab close, restrict when isDeveloper | Bhavesh | 14 | 2 | change method for realse version | Issue | Done | 2018-03-05
Week 10 | 5835 | 5835 - NG General - typeahead doesn't show all values | Bhavesh | 8 | 1 | Design changes for textbox | Enhancement | Done | 2018-03-05 | KPI 1 | 5907
Week 10 | 5880 | NG General - Provide handler for clicking a notification tile | Bhavesh | 1 | 1 | change in header tile component for flip functionality | Issue | Done | 2018-03-06
Week 10 | 5907 | 5907 - Textbox with valuelist issue | Bhavesh | 14 | 7 |  | Issue | InProgress | 2018-03-06 | KPI 2
Week 10 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 4 |  | Enhancement | Done | 2018-03-05
Week 10 | 5877 | 5877 - NG - Datagrid UI related | Rakesh | 2.5 | 2 |  | Enhancement | Done | 2018-03-05
Week 10 |  | Control visibility issue in sales order (warehouse) | Rakesh | 1.5 | 1.5 |  | Issue | Done | 2018-03-05
Week 10 | 5888 | 5888 - NG - Panel height Related Issue in Article Form and Others | Rakesh | 20 | 6.5 |  | Issue | InProgress | 2018-03-06 | KPI 3
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 8 | worked on globis portal for dynamic login and menu related stuff | Enhancement | InProgress | 2018-03-05
Week 10 | 5888 | 5888 - NG - Panel height Related Issue in Article Form and Others | Nilav | 16 | 4 |  | Issue | InProgress | 2018-03-06
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 4 | Feneko portal : Worked on menu related stuff, displaying menu as per user role, update menus in database after debugging for console flag. | Enhancement | InProgress | 2018-03-06
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 4 | Feneko portal : worked on sales order details and listing page, fetching data and displaying in grid. | Enhancement | InProgress | 2018-03-06
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 6 | Feneko portal : worked on sales order details and listing page, sales order line listing form. | Enhancement | InProgress | 2018-03-07
Week 10 | 5924 | 5924 - NG - dataProviderID correction in components | Nilav | 2.5 | 2 |  | Issue | Done | 2018-03-07
Week 10 | 5924 | 5924 - NG - dataProviderID correction in components | Bhavesh | 2.5 | 2.5 |  | Issue | Done | 2018-03-07
Week 10 | 5907 | 5907 - Textbox with valuelist issue | Bhavesh | 14 | 5.5 | setting Validation and tabindex | Enhancement | Done | 2018-03-07 | KPI 2
Week 10 | 5844 | 5844 - NG - Contracts - Form Conversion | Pramod | 32 | 3.5 |  | Enhancement | Done | 2018-03-05
Week 10 | 5918 | 5918 - NG - Warehouse - Warehouse Location, Warehouse Move, Put Rules, To Delivery, etc... | Pramod | 26 | 5 |  | Enhancement | Done | 2018-03-05
Week 10 | 5918 | 5918 - NG - Warehouse - Warehouse Location, Warehouse Move, Put Rules, To Delivery, etc... | Pramod | 26 | 5 |  | Enhancement | Done | 2018-03-06
Week 10 | 5919 | 5919 - NG - Complaint forms conversion | Pramod | 7 | 4 |  | Enhancement | Done | 2018-03-06
Week 10 |  | Sales order form Redesign | Pramod | 0.5 | 0.5 |  | Enhancement | Done | 2018-03-07
Week 10 | 5924 | 5924 - NG - dataProviderID correction in components | Pramod | 2.5 | 2.5 |  | Enhancement | Done | 2018-03-07
Week 10 | 5918 | 5918 - NG - Warehouse - Warehouse Location, Warehouse Move, Put Rules, To Delivery, etc... | Pramod | 26 | 5 |  | Enhancement | Done | 2018-03-07
Week 10 | 5943 | 5943 - NG - Warehouse - Form conversion for the to pack without tracking, warehouse stock, inventory, etc... | Pramod | 17 | 3 |  | Enhancement | Done | 2018-03-08
Week 10 |  | Functional Flow Related | Pramod | 18 | 6 |  | Enhancement | Done | 2018-03-08
Week 10 | 5943 | 5943 - NG - Warehouse - Form conversion for the to pack without tracking, warehouse stock, inventory, etc... | Pramod | 17 | 3.5 |  | Enhancement | Done | 2018-03-09
Week 10 | 5937 | 5937 - NG - No limitation on data length in a field? | Pramod | 12 | 5 |  | Enhancement | Done | 2018-03-09
Week 10 | 5917 | NG General issues - bar main functionalities does not move when minimizing the top bar | Bhavesh | 5 | 5 |  | Issue | Done | 2018-03-08
Week 10 | 5931 | NG - Screen title bar disappears on home (dashboard) screen | Bhavesh | 1 | 1 | minucrumb visibility issue when tab change | Issue | Done | 2018-03-08
Week 10 | 5928 | NG - Valuelist type ahead | Bhavesh | 5 | 2 |  | Issue | Done | 2018-03-08
Week 10 | 5917 | NG General issues - bar main functionalities does not move when minimizing the top bar | Bhavesh | 5 | 5 |  | Issue | Done | 2018-03-09
Week 10 | 5928 | NG - Valuelist type ahead | Bhavesh | 5 | 3 |  | Issue | Done | 2018-03-09
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 4 | Worked on sales order details page for feneko portal | Enhancement | InProgress | 2018-03-08
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 4 | Worked on listing pages for sales order line, sales invoice, sales invoiceline, delivery, delivery line | Enhancement | InProgress | 2018-03-08
Week 10 | 5857 | 5857 - Feneko Portal | Nilav | 128 | 8 | Worked on sales invoice detail and list page, sales invoice line details page, delivery details page. | Enhancement | InProgress | 2018-03-09
Week 10 | 5924 | 5924 - NG - dataProviderID correction in components | Rakesh | 2.5 | 0.5 |  | Issue | Done | 2018-03-07
Week 10 | 5888 | 5888 - NG - Panel height Related Issue in Article Form and Others | Rakesh | 20 | 5 |  | Issue | InProgress | 2018-03-07 | KPI 3
Week 10 | 5888 | 5888 - NG - Panel height Related Issue in Article Form and Others | Rakesh | 20 | 7 |  | Issue | InProgress | 2018-03-08 | KPI 3
Week 10 | 5830 | 5830 - NG General issues - suggestions attachment functionality | Rakesh | 28 | 2 |  | Done | Done | 2018-03-08
Week 10 | 5888 | 5888 - NG - Panel height Related Issue in Article Form and Others | Rakesh | 20 | 6 |  | Issue | InProgress | 2018-03-09 | KPI 3
Week 10 | 5900 | 5900 - Article Type Issue | Jay | 3 | 3.5 |  | Issue | Done | 2018-03-06
Week 10 | 5873 | 5873 NG General - refresh data behaviour | Jay | 30 | 5.5 |  | Issue | Done | 2018-03-06
Week 10 | 5873 | 5873 NG General - refresh data behaviour | Jay | 30 | 8 | Issue related to refresh + fix for filtering in the viewer form | Issue | InProgress | 2018-03-07
Week 10 | 5873 | 5873 NG General - refresh data behaviour | Jay | 30 | 4 | Issue related to refresh | Issue | InProgress | 2018-03-08
Week 10 |  | Meeting | Jay | 2.5 | 2.5 | Meeting + Demo | Enhancement | Done | 2018-03-08
Week 10 | 5873 | 5873 NG General - refresh data behaviour | Jay | 30 | 8 | Issue related to refresh + fix for the issue related to Multiselect to delete | Issue | InProgress | 2018-03-09
Week 10 | 5947 | 5947 - NG General - Bug in expanding tabs when showing same form in different tabs | Rakesh | 8 | 2 |  | Issue | InProgress | 2018-03-09

## Planning Overview (hidden)
DATE | Planning Overview | Position | BASELINE
2016-05-02 | Project Start | 25 | 1
2016-06-02 | User Management (inc Shanghai) | 10 | 1
2015-05-20 | Sailing Schedule | -10 | 1
2015-05-19 | Warehouse (WHS) | 15 | 1
2016-07-30 | Delivery 1 | 15 | 1
2016-09-23 | Quotation & Request Quote (LCL & FCL only) | -15 | 1
2016-09-01 | Tariff | 15 | 1
2016-12-01 | Delivery 2 | 15 | 1
2017-01-12 | Booking & quote to booking(LCL & FCL only) | -20 | 1
2017-02-20 | Delivery 3 | 20 | 1
2017-04-02 | Final Delivery | -15 | 1
2017-05-09 | Defect Fixing & Hotfix / Release Updates | 15 | 1

## Legend (hidden)
Types of Gantt | Symbols to be used for % complete
Planned | █
Actual | █
█
Note on D6: This one lets you disable the completion status